RTM View Shell

Historical Reports — Project Plan

From design to deployment

Module owner: BI specialist (role-bi) · Coordinator-orchestrated

v1.1 · 2026-06-20 · RTM View Shell

Every code task = CC prompt → coordinator §4-review → native CC, commit, no push. Contour touches (RTSData_*/RTM Engine) = operator-gated.

# Document revision history

| Version | Date | Summary of changes | Product release ID | Shipped-with (commit/barrier) |
| --- | --- | --- | --- | --- |
| 1.0 | 2026-06-19 | Initial project plan — Historical Reports module, design to deploy | RTM-REL-2026.06 | (pending push) |
| 1.1 | 2026-06-20 | B3 IN (create call-id/WTUUID linkage for full AHT); agent AHT full via StatusId (Hold∈ONPHONE); identity rule → CLAUDE.md §46 | RTM-REL-2026.06 | (pending push) |

# Contents

# 0.  Foundations (locked)

Two-tier data architecture (architect verdict) RT-tier (RTSData_*): windowed ~1-month retention via the module’s OWN reliable purge. RTSData_MidnightClear is dead code (Engine.cs:957 commented) — NEVER re-enable. Historical tier (hist_*): 6–7 year retention, monthly RANGE partitions. The aggregator moves RT → historical BEFORE data ages out of the RT window.

Verified column contract (schema.sql): RTSData_Interaction = Workgroup / UserId / TimeInQueue / TalkTime / IsAnswered / IsAbandoned / InQueueDateTime (NO Handle/ACW/Hold). Queue join NGC_Queues.ExternalId = Workgroup. Agent source RTSData_UserStatusLog (Duration + StatusGroup + Start/End).

Identity rule (B5): Queues + Agents = EXTERNAL contact-centre identifiers; system users = INTERNAL uuid. Agents are NOT keyed on ApplicationUser.

Operator decisions:

- B1 = A — partitions from v1 (EF + raw-SQL monthly RANGE). The “audit pattern” is doc-fiction (audit_logs is a plain table) — partitioning is net-new either way.

- B2 = CONTOUR — decide RTSData_* purge now (scheme i): windowed purge on the RTM tables. Operator-gated per apply.

- B3 = IN — create a call-id (WTUUID) in RTSData_UserStatusLog + RTM Engine stamps it → join Interaction↔UserStatusLog → full per-call AHT. Contour change (A3), operator-gated; bi+backend design.

- B4 = staffing empty in v1 — queue AgentsStaffed/Ready/Busy deferred to v2.

- B5 = identity rule — external agent/queue ids; drop login→ApplicationUser resolution for agents (now CLAUDE.md §46).

- AHT (corrected): Hold is a STATUS in the ONPHONE group → agent AHT = Talk+Hold+ACW from RTSData_UserStatusLog at StatusId level (no contour). Full per-call QUEUE AHT needs the call-id/WTUUID linkage (B3).

# 1.  Roles — who does which part

| Part | Owner (authors) | Review-gate | Notes |
| --- | --- | --- | --- |
| Module orchestration, data model, aggregator, repo, CQRS | bi | coordinator §4 | leads; owns Historical/** + HistoricalReports/** |
| DB migrations (hist_*/user_reports, partitions) | bi → dba review | dba | EF-only; raw-SQL for PG partitioning |
| RT purge on RTSData_* (B2) + WT.UUID write (B3) | bi design → backend (RTM) | operator gate + dba | CONTOUR — operator-confirm per apply |
| UI (filter bar, table, tiles, pages, builder), CSV, i18n | shell (spec from bi) | security + §4 | shell territory |
| Aggregation BackgroundService | bi / backend | §4 | server-side, reads RTM tables read-only |
| Multitenant isolation, PG-filter, Viewer-cannot-create | — | security | review gate, no territory |
| Module documentation | techwriter | doc gate | after features land |
| Packaging, deploy scripts, Compare | devops | — | reuses lesson-complete Update-RTMView |
| §4-review, push barriers, claim arbitration | coordinator | — | orchestration |

Sub-claims (no overlap): bi = Historical/** + HistoricalReports/** + HistoricalAggregationService + Components/Reports/** + Pages/Reports/** + hist_*/user_reports migrations; shell = the Report .razor/.css it builds + Reports.* resx; dba = reviews migrations (file-claim at task time); backend = RTM/RTM/*.cs for B2/B3.

# 2.  Phase 0 — Design finalization (now)

- bi revises the data model per B5 (external agent keys; drop ApplicationUser resolution).

- bi folds B1 (partitions-from-v1) + B2 (RTSData_* purge sub-track) + evaluates B3 (WT.UUID feasibility with backend).

- bi authors tools/cc_prompt_hist_001.md → coordinator §4-review → on PASS, issue.

- Operator verdict on B3 (adopt WT.UUID in v1, or defer to v2) after bi+backend feasibility.

- Exit: §4-blessed CC-HIST-001 prompt + B3 verdict.

# 3.  Phase 1 — v1 build

## Track A — CC-HIST-001 Data Layer  (bi authors · dba review · §4 · security)

- EF migration: hist_queue_intervals + hist_agent_intervals + user_reports — monthly RANGE partitions (B1=A, raw-SQL), TenantId + GQF, indexes.

- HistoricalAggregationService (BackgroundService) — read-only on RTSData_*/NGC_*; idempotent DELETE-window+INSERT; bucket by InQueueDateTime; agent agg = SUM(Duration) per StatusGroup; external agent ids (B5); aggregated-through watermark.

- IHistoricalReportRepository + EF impl (AsNoTracking; pg_queues filter in repo; NULLIF metrics).

- MediatR Q1/Q5/A4/A5 + DTOs + FluentValidation.

- >=6 unit tests (idempotency, NULLIF, unmatched→NULL+raw kept, bucketing, tenant isolation, SL threshold).

## Track A2 — RT-tier purge (B2, CONTOUR — operator-gated)

Touches the RTM external contour Operator confirmation required before ANY apply to RTSData_*. Windowed ~1-month purge/partitions on the RTM tables (scheme i); coordinate RTM Engine; no MidnightClear collision (dead code Engine.cs:957). Mark every contour-touch.

## Track A3 — call-id/WTUUID linkage (B3, CONTOUR — IN, operator-gated)

The call-id does NOT exist yet in RTSData_UserStatusLog (verified schema). CREATE it: add a call-id column + RTM Engine stamps the active call’s id per status row; join UserStatusLog↔RTSData_Interaction on call-id+Workgroup → full per-call AHT (Talk+Hold+ACW). KEY feasibility (backend): the status feed carries no call-id — Engine must reliably know the active call at status-change (risk on transfer/consult). Contour, operator-gated per apply; bi design + backend (RTM) + dba migration.

## Track B — CC-HIST-002 UI Layer  (shell · bi spec · §4 · security)

- ReportFilterBar, ReportTable, ReportSummaryTiles (Blazor; dark/RTL/a11y).

- Pages: Q1, Q5, A4, A5, ReportsIndex + NavMenu “Reports”.

- CSV export (server C# + JS blob); i18n Reports.* (en-US/ru-RU[/he-IL]); reports.css; >=4 UI tests.

- Depends on Track A queries.

## Track C — CC-HIST-003 User Reports  (bi + shell · §4 · security)

- UserReport entity + EF config + repo + CQRS (Save/Delete/Get/Run).

- ReportBuilder 4-step wizard + UserReportsList + CustomReportPage.

- Seed 17 system reports (IsSystem=true) in DatabaseInitializer.

- Security: Viewer-cannot-create, IsPublic, PG-filter enforced in Application layer. Depends on Track A repo.

# 4.  Phase 2 — Integration & verification

- All tracks build green; unit (>=6) + UI (4) + integration (aggregation idempotency, tenant isolation) + security tests.

- coordinator §4 per prompt; security review; techwriter module docs (user/admin guide).

- Acceptance: /reports renders; Q1/Q5/A4/A5 show data; builder saves/runs; CSV exports; aggregation populates hist_*; (B2) RT purge bounds RTSData_*.

# 5.  Phase 3 — Deploy prep & release  (devops · dba · coordinator · operator)

- dba: export DB module (Export-All) → schema.sql + new migrations (hist_*/user_reports[/RTSData_* purge]).

- devops: package (lesson-complete Update-RTMView + new migrations) — all 4 today’s fixes baked.

- coordinator/operator: push barrier for the BI commits (+ the 6 already unpushed).

Mandatory deploy discipline (today’s norm) MANDATORY Compare-ToBaseline BEFORE deploy, per server. Never by memory; each server its OWN -MigrationList. Then: pg_dump backup → E1 gate → apply (postgres, ordered) → binaries → start → Compare-after. Any tool error → STOP + rollback from backup. Per server: 234, 45…

# 6.  Phase 4 — Post-deploy verify

- Compare-after (drift closed); smoke (/reports + each report + builder + CSV); aggregation running; (B2) RTSData_* bounded.

# 7.  Dependencies & gates (critical path)

Phase 0 (bi + §4) → Track A (data layer) → { Track B (UI), Track C (user reports) in parallel } → Phase 2 (integration) → Phase 3 (deploy) → Phase 4 (verify).

- Track A2 (RTSData_* purge) + A3 (WT.UUID) = CONTOUR, parallel but operator-gated; off the v1 critical path unless B3 adopted for v1.

- Every code task: CC prompt → §4 → native CC → commit (no push). Pushes only at the Phase-3 barrier.

- Operator decision points: B3 adopt v1/v2 (Phase 0); each RTSData_* contour apply (A2); push barrier; deploy go per server.

# 8.  Open risks

- AHT: agent AHT full via StatusId (Hold∈ONPHONE); full per-call queue AHT via A3/B3 call-id linkage — risk = Engine reliable stamp on transfer/consult.

- Partitioning is net-new (audit pattern is doc-fiction) — dba designs RANGE + create-ahead/drop-aged carefully.

- Identity match (B5): confirm RTM UserId vs external agent id population on 234/45 (empirical) before relying on agent keys.

- RTSData_* unbounded growth is bounded ONLY by A2 (contour) — until applied, growth continues.