Project Launch Runbook

Cowork multi-session project bootstrap

From “create a project” to the coordinator’s “team up & ready” report

For the Operator, Coordinator, and Curator

Edition EN · 2026-06-11 · Reusable, product-agnostic methodology

# Document revision history

This table lists the revision history of this document.

| Version | Date | Summary of changes | Product release ID | Shipped-with (commit/barrier) |
| --- | --- | --- | --- | --- |
| 1.0 | 2026-06-11 | initial runbook | RTM-REL-2026.06 | (pending push) |

# Contents

# Purpose & audience

This runbook captures the proven process for launching a new Cowork project as a multi-session team: one operator, one coordinator, an optional external curator, and a set of specialist sessions. It exists so a new project can reach a credible “team up & ready” state quickly and safely, with the same discipline that keeps a long-running project honest.

Audience: the Operator (directs the project), the Coordinator (owns the bus and the gates), the Curator (external source-of-truth / certifier, when present), and specialists being onboarded.

# How to use this runbook

- Work the six phases P0 → P5 in order. Each phase has a Goal · Who · Actions · Artifacts · Verification gate · Operator GO.

- Every gate is verified against the object store / repo walk, never from a chat claim.

- Copy the Appendix templates (A–E) and fill the placeholders.

- The cross-cutting invariants in section 5 are binding throughout.

# 1. Roles & responsibilities

| Role | Mandate | Owns | Gate it holds |
| --- | --- | --- | --- |
| Operator | Directs the project; the only one who pushes and gives GO; schedules session turns. | Product intent, roster, GO/NO-GO, pushes. | Every phase GO. |
| Coordinator | Runs the bus and the process. | CLAUDE.md §0 + coordination + command-registry, .coord/ bus, claim-map, commit serialization, push barrier, work-done map, the ready report. | P1–P5 gates. |
| Curator | External SME / source capture; certifies “core raised” by an object-store walk. | Curation channel, certification. | P1 core-raised certification. |
| Specialists | Module owners (backend, frontend, DB, devops, …); do the work within their claims. | Their module paths. | Their READY/HOLD at barriers. |
| Security | Mandatory cross-cutting gate. | Security review. | Mandatory ACK before any prod release. |
| Tech Writer | Documentation gate and author. | docs/** authoring, DOCS inventory, approved/editing governance. | Doc-sync impact-triage ack in the push quorum. |

# 2. The six-phase model

Each arrow crosses a verification gate confirmed by walking the repo / object store.

P0 Universe -> P1 Core -> P2 Roster & Claims -> P3 Tree hygiene -> P4 Work-done map -> P5 Ready (operator) (coord) (coord + operator) (coord/CC) (coord) (coord)

# 3. Phases

## P0 — Universe (the empty world)

Goal: a mounted, version-controlled project folder with a seed spec.

Who: Operator.

Actions:

- Create or connect one Cowork project folder; record its single absolute working path (the working-folder rule — all reads and writes use exactly that path).

- git init; create the working branch; pick a short session prefix (e.g. BY-AD) used by every session and chat.

- Seed CLAUDE.md with the product spec: product, stack, scope / out-of-scope, working-folder path, session prefix.

- Commit the baseline.

Artifacts: repo (.git), branch, seed CLAUDE.md, the working-folder rule.

Verification gate git log shows the repo; the folder is mounted; CLAUDE.md is present (object-store check).

Operator GO: → build the core.

## P1 — Core (discipline + bus)

Goal: the binding §0 discipline, the coordination protocol, and the .coord/ bus exist.

Who: Coordinator.

Actions:

- Extend CLAUDE.md §0 (BINDING) — see Appendix A: 0.1 verify; 0.2 resume-integrity; 0.3 Python + os.fsync writes, Edit tool BANNED on the mount; 0.4 pre-commit check; 0.5 mount .git/status UNRELIABLE → object-store verify; 0.6 NO auto-push and you cannot push from the mount [L-SC-20]; 0.7 post-commit re-sync from HEAD (PD-007).

- Add the multi-session coordination section + a command registry.

- Build the .coord/ bus (Appendix B).

- Write one init-prompt per planned specialist (Appendix C); tag not-yet-active roles FROZEN / NOT-YET-EXISTS.

Artifacts: CLAUDE.md §0 + coordination + command-registry; .coord/ bus; init-prompts.

Verification gate The curator certifies by object store (not chat) — §0 anchors present, bus files exist, init-prompts carry the mandatory blocks.

Operator GO: → raise the roster.

## P2 — Roster & Claims

Goal: a validated, non-overlapping claim-map.

Who: Coordinator (+ operator confirms the roster).

Actions:

- Operator confirms the initial roster.

- Build the claim-map (Appendix D): module → paths, seam rules, READ-ONLY / no-touch zones.

- Validate against the real tree: do the paths exist? nesting? overlaps?

- The roster is NOT frozen — the operator may split a role or activate one mid-bootstrap; re-validate on every change.

- Share a cross-cutting asset (e.g. DB migrations) by OWN / REVIEW / APPLY across three roles — never by carving a sub-path out of another owner’s claim.

Artifacts: claim-map, seam rules.

Verification gate real paths, ZERO overlap, a single owner per seam.

Operator GO: → tree hygiene.

## P3 — Tree hygiene

Goal: a clean, intentional, committed tree.

Who: Coordinator issues CC tasks; specialists run them (native CC, not the mount).

Actions:

- Commit .gitignore FIRST, then re-check status.

- Decide tracked vs ignored BEFORE any blanket add: legacy / large dirs → .gitignore (or LFS by owner call); logs → ignore; DB dumps → owner call; word-lock ~$ files → discard.

- De-duplicate documents ONLY by a verified subset proof (textual diff: drop X only if X is a subset of Y with zero unique lines).

- Commit existing work in labeled, module-grouped commits — native git / CC (the mount can’t commit), serialized by commit.lock, journaled, with a post-commit re-sync from HEAD.

Artifacts: .gitignore, module-grouped commits, journal lines.

Verification gate git status clean; every commit journaled.

Operator GO: → work-done map.

## P4 — Work-done map

Goal: an honest map of what actually exists.

Who: Coordinator.

Actions:

- Build the map by walking the committed tree, labeling each item Intended / Drafted / Delivered (verified) / Committed (hash).

- Delivered (verified) requires a green build/test — a commit is not “Delivered”.

- Distribute the first tasks per the claim-map (via the dispatch loop, section 4).

Artifacts: work-done map, first task assignments.

Verification gate the map is built from the repo, not chat; every “Delivered” is backed by a build/test.

Operator GO: → ready.

## P5 — Ready

Goal: the team is up and the first work is moving.

Who: Coordinator.

Actions:

- Write the “team up & ready” report (Appendix E) — a Definition-of-Done checklist that includes the claim-map and confirms that each “Delivered” item was verified by the object store (git cat-file / git show / git hash-object), not chat.

Artifacts: the “team up & ready” report.

Verification gate the report’s credibility is the object-store proof behind every “Delivered” claim, plus a defined push barrier + quorum (incl. the mandatory Security ack and the Tech-Writer doc-sync ack).

Operator GO: → the project is launched.

# 4. Operational loop — task dispatch (the heartbeat after launch)

Once the team is stood up (P5), this is how work actually moves. It is operator-mediated: the coordinator routes, the operator triggers, the specialist executes.

- The coordinator drafts a full, self-contained directive (a compose-directive routing action — not a base session-coord §10 verb; a project may register its own): mandatory reads + the integrity block + the specialist’s claim + the task + acceptance criteria + commit.lock / journal / no-push. Code work points at a tasks/<file>.md (CC-only code rule).

- The coordinator writes the directive into that specialist’s inbox .coord/inbox/<slug>.md (its router duty). It does not execute it and does not trigger the session.

- The coordinator hands the operator a trigger-list: the session slugs to activate (e.g. backend-0611, security-0611).

- The operator runs the intake command (коорд: входящие) in each named session. That session reads its own inbox inbox/<slug>.md and does the work via CC.

- The specialist reports back to the coordinator via inbox/coordinator-<slug>.md; it marks a message handled only as its recipient.

- The coordinator on its next intake reads its inbox, journals the outcome, and routes the next step.

Three roles in one line: Coordinator = router (stages directives, reviews, journals — writes no feature code, never “sends” by triggering). Operator = the trigger (activates each session). Specialist = executor (reads its own inbox, does the CC work, reports).

coordinator --writes directive--> inbox/<slug>.md coordinator --trigger-list--> OPERATOR OPERATOR --intake in session--> specialist --reads own inbox, CC work--> commit (commit.lock + journal, no push) specialist --report--> inbox/coordinator-<slug>.md --> coordinator (next intake) --journal--> next task

Verb precision. The registry lists the intake verb as the coordinator reading an inbox; operationally the operator uses the same intake verb in every session to mean “read my inbox and act” (in a specialist session, “my inbox” = inbox/<that-slug>.md). Cite as canonical only the verbs in the session-coord §10 registry; describe project-specific verbs as patterns or add them to §10.

Invariants of the loop All code changes go out as CC prompts (CC-only rule); the coordinator analyses / plans / reviews / journals only. A handled-marker is written only by the recipient of a message. Commits run under commit.lock, are journaled, and never auto-push.

# 5. Cross-cutting invariants (binding throughout)

- Verify, not chat — tool success ≠ delivery; build status tables by walking the repo (§0.1).

- Python + os.fsync for every write; the Edit tool is BANNED on the mount (§0.3).

- Object-store verification — the mount’s .git / git status is unreliable; confirm with git hash-object vs git rev-parse HEAD:<file>; never escalate “corruption” from a mount read (§0.5).

- No auto-push; you cannot push from the mount — every push is a conscious operator decision via the dedicated push prompt [L-SC-20] (§0.6).

- Post-commit re-sync from HEAD — counteract the mount’s async cache write-back (PD-007, §0.7).

- commit.lock covers the plumbing path too — the commit-tree + direct ref-write path has no git-level locking; never bypass commit.lock.

- Handled-markers are written only by the recipient of a message.

- The two-Cowork cross channel is deferred until a second Cowork instance actually exists.

- Documentation governance — a coordinator-assigned Product Release ID scheme RTM-REL-YYYY.MM[.patch] + a Shipped-with column; a doc-sync impact-triage gate in the push quorum; and the approved/{doc,pdf} + editing/ layout with a mandatory revision-history table.

# 6. Case study & lessons — Agent Desktop bootstrap

Worked example. Project: Agent Desktop / Bynet — a Cisco UCCE/UCCX agent desktop via Finesse; .NET 8 backend, frontend added later. Captured by the curator; use it as the concrete illustration — the normative steps are sections 1–5 above.

## Timeline

- M0 — the curation channel is established, separate from the active coordinator bus; curator and project inboxes are set up.

- M1 — curator Q&A; the claim-map is corrected against the real tree (3 fixes) plus a tree-hygiene precondition.

- M2 (operator GO) — core raised, verified by a curator object-store walk: CLAUDE.md v1.8 (1054 lines) with §0.5/0.6/0.7, the multi-session protocol, and the command registry; the .coord/ bus (14 files); 5 init-prompts (frontend tagged FROZEN + NOT-YET-EXISTS). Boundary honored — only .coord/ touched, no commit/push.

- M3 — pre-hygiene curator review; init-prompts certified; tree-hygiene labeling guidance issued.

- M4 — full roster up (7 sessions). The operator changes the roster mid-bootstrap: DBA/Devops split into two roles; frontend un-frozen (first task = a React + Vite + MUI scaffold); the prefix is locked BY-AD. A Step-0 gate passes: a duplicate spec doc is resolved by a textual-diff subset proof (a is a subset of c, zero unique) before deletion. The coordinator chat migrates mounts; live state is kept in coordinator_handoff.md.

- M5 (in progress) — tree hygiene is a CC job (the mount physically cannot commit: a stuck .git/index.lock, and bindfs denies rm/rename inside .git → [L-SC-20] proven). It awaits native CC for three module-grouped, labeled commits; then the work-done map (build + test before any “Delivered” label).

## Lessons (generalize for any project)

- The roster is not frozen at the roster phase — re-validate the claim-map for overlap on every operator change.

- Share a cross-cutting asset by OWN / REVIEW / APPLY across roles, never by carving a sub-path out of an owner’s claim.

- De-duplicate documents only by a verified subset proof (X subset of Y, zero unique), never by assumption.

- The mount cannot commit/push (stuck .git locks; bindfs denies rm/rename in .git) — all commits run native CC, serialized by commit.lock, journaled, with a post-commit re-sync. [L-SC-20].

- Certify “core raised” by walking the repo via the object store, never from a chat claim.

- A handled-marker is written only by the recipient of a message.

- A cross-project channel that depends on both mounts breaks on remount — route each direction through a file in the writer’s own bus, read by the party that holds both mounts (the curator).

## Tree-hygiene numbers (from the worked example)

Dirty tree at start: 3 modified + 23 untracked. Sequence: commit .gitignore first → re-check; decide tracked-vs-ignored before any blanket add (legacy ~750 MB → .gitignore, no LFS; production logs → ignore; root SQL dumps → DBA call; word-lock ~$ files → discard; spec docx → docs/); then module-grouped labeled commits; a build/test gate before labeling any feature “Delivered”.

# Appendix A — CLAUDE.md skeleton

Copy and fill the placeholders. §0 is binding.

# <PROJECT> — CLAUDE.md > Single source of truth for autonomous work. Working folder: <ABSOLUTE WORKING PATH>. Session prefix: <PREFIX>. ## 0. Environment rules — executor must read first (BINDING) ### 0.1 Verification — tool success != delivery Verify via ls / git log / Read before claiming anything exists or is delivered. Build status by walking the repo. ### 0.2 Session-resume integrity On resume: git status --short; for each M file check truncation; restore via: git show HEAD:<f> > <f>. ### 0.3 Writes: Python + os.fsync ONLY; the Edit tool is BANNED on the mount Every write: read -> modify -> write with f.flush(); os.fsync(f.fileno()); then verify with tail -3 and wc -l. ### 0.4 Pre-commit check Run the pre-commit verifier before every git add / commit; on FAIL restore from HEAD and retry. ### 0.5 Mount .git / git status is UNRELIABLE -> object-store verify Confirm tracked-state and content via git hash-object <f> vs git rev-parse HEAD:<f>. Never escalate corruption from a mount read. ### 0.6 No auto-push; you cannot push from the mount [L-SC-20] Never git push automatically; pushes are an operator decision via the dedicated push prompt. ### 0.7 Post-commit re-sync from HEAD (PD-007) After every commit, re-sync committed files from HEAD as the last action (counteracts cache write-back). ## <N>. Multi-session coordination State bus in .coord/; claims by module; commit.lock serializes commits (covers the plumbing path); journal every commit; push barrier with quorum (mandatory Security ack + Tech-Writer doc-sync ack). Handled-markers by recipient only. ## <N+1>. Command registry <list each operator command verb and its exact semantics>

# Appendix B — .coord/ bus files

.coord/ README.md # what the bus is + quick reference .gitignore # ignore the runtime state below sessions/<slug>.md # one per active session (frontmatter below) locks/commit.lock # exclusive commit token (repo-wide) journal.md # append-only commit log inbox/<slug>.md # directed messages TO a session/role (coordinator-<slug>, curator, ...) coordinator_handoff.md # live resume artifact for a fresh coordinator push/ request.md # active barrier (freeze); tombstone when cleared acks/<slug>.md # per-session READY / HOLD

Session file frontmatter:

--- session: <Name> slug: <role>-<MMDD> role: <role> status: active # active ¦ pushing ¦ done modules: [<module>] # claimed modules files: [] # optional file-level claims heartbeat: <UTC> cc_task: none --- <one-paragraph charter>

Inbox message block (handled-marker by the recipient only):

## <UTC> ¦ from: <slug> ¦ to: <slug> <body> --- > handled <UTC> by <recipient-slug> — <what was done>

# Appendix C — Init-prompt template (per specialist)

<PREFIX>: you are the standing <ROLE> specialist. Session name "<Name>". 0. COMMS: your inbox = .coord/inbox/<slug>.md (read it whole; mark each block handled). Your outbox = the COORDINATOR's SLUG inbox .coord/inbox/coordinator-<slug>.md. All .coord/ and work writes via Python + os.fsync. Commands per the session-coord skill section 10 — never guess an unknown verb. 1. INTEGRITY (0.2): git status; for M files hash-object vs HEAD; restore truncated. 2. MATERIAL: read CLAUDE.md section 0 + coordination + your domain sections. 3. TERRITORY: you OWN <paths> (claims); READ-ONLY elsewhere; shared seams via OWN / REVIEW / APPLY. 4. REGISTER: write .coord/sessions/<slug>.md, status active. 5. READ BUS: your inbox; sessions/*; journal tail; push/request (if FREEZE -> stop). 6. PUSH QUORUM: give READY / HOLD on your paths at every barrier. 7. CONFIRM: flush an ack to the coordinator's slug inbox + a short chat reply.

# Appendix D — Claim-map template

# Claim-map — <PROJECT> ¦ Module ¦ Owner (slug) ¦ Paths (claims) ¦ Seam rule ¦ Read-only / no-touch ¦ ¦---¦---¦---¦---¦---¦ ¦ <module> ¦ <role>-<MMDD> ¦ <paths> ¦ OWN / REVIEW / APPLY where shared ¦ <paths others own> ¦ Validation: every path exists in the real tree; ZERO overlap; one owner per seam. Re-validate on any roster change.

# Appendix E — “Team up & ready” report template

# Team up & ready — <PROJECT> (<date>) Definition of Done: - [ ] Core: CLAUDE.md section 0 (0.1-0.7) + coordination + command-registry — object-store verified. - [ ] Bus: .coord/ files present (README, sessions/, locks/, journal, inbox/, push/). - [ ] Roster holding: sessions registered; claim-map attached; ZERO overlap. - [ ] Tree clean: git status empty; commits journaled. - [ ] Work-done map attached; EACH “Delivered” verified by object store (cat-file / show / hash-object), not chat. - [ ] First tasks issued per the claim-map. - [ ] Push barrier + quorum defined, incl. MANDATORY Security ack (+ Tech-Writer doc-sync ack). - [ ] First CC task ran clean. Operator GO: ____

Sources: in-repo CLAUDE.md §0 / §42 / §44, the live .coord/ bus, and the session-coord skill (normative methodology); the Agent Desktop bootstrap capture by the curator (case study). EN canonical; a ru edition follows on request.